October 23, 2000

Mike Robbins

Post Properties

# RE:	AC II-B Public Infrastructure / Streets and Utilities

VIA FACSIMILE  to  (972) 726-0562

As a result of the October 18th walk-through, attended by you, Jeff Gibson (Gibson & Assoc.), David Meyers (HZ), Ron Lee, Parks Superintendent, and myself, the following items are to be remedied:

- At the NE corner of Morris and Artist Way, there is a trip hazard at the bottom right of the pedestrian ramp.

- Clean up any concrete “spoil” throughout project.

- Clean up and re-do street joint sealer as needed.

- Seal curb cuts throughout project.

- Clean up any sealer spillage throughout project.

- Complete joint sealing at West end of Morris, North end of Artist, and Goodman Ave.

- Replace / repair street signs at Morris and Paschal.

- Replace stop bar at southbound Paschal.

- Clean concrete splatter off of “no parking” sign on Paschal and as needed throughout project.

- Broken concrete at second tree-well on west side of Paschal.

- Clean all fire hydrants in preparation for city crews to paint.

- Reset storm drain inlet ring and cover on Artist Way east side, north of Goodman.

- Area storm drain inlet at Artist Way and Fire Lane, grade incorrect?

- Clean out water meter boxes and place pea gravel per specification.

- Submit test reports for all irrigation DCVA’s.

- Pump out and clean meter vaults.

- Fill “lifting pin” holes on meter vaults with cementitious grout or epoxy.

- Private irrigation meter Bldg. A needs stainless steel bolts per specification.  Check all.

- Complete sign mounting and finial placements.

- Clean out all storm drain inlets.

- “No Parking, This Side of Sign” at NE corner of Artist Way and Goodman is on the wrong side of the pole.

- Speed Limit sign on SB Artist Way to be relocated to N side of tree-well.

- Speed Limit sign WB Morris west of Artist Way to be relocated west to blue X on paver.

- Grade and establish ground cover on all adjacent slopes on Goodman and Artist Way.

David E. Wilde, Public Works Inspector

Ecc:	Lynn Chandler, Building Official

Robin Jones, Street Superintendent

Ron Lee, Parks Superintendent

Michael Murphy, Director of Public Works

Keith Thompson, Utilities Foreman