June 5, 1998

Mr. A.E. Henry

Henry Building, Inc.

2450 N. Beckley Rd.

P.O. Box 279

Lancaster, TX  75146

Re:  N.T.A. Plaza, 4949 Keller Springs Rd., Addison, TX.

Dear Mr. Henry:

At your request, the Town of Addison Public Works Department met your representative, Charlie Smith, and performed a walk through of the public works infrastructure at the above referenced property.

We have received one Mylar and two blue line sets of plans, a list of material quantities, and backflow device test reports from you or your representatives.

The following items were discussed and are to be completed prior to final acceptance by the Town of Addison:

- Revision of sidewalk ramps at drive approaches to ADA specifications.

- Lower fire hydrant at south side of property 6” and set grade to ground level markings on barrel.

- Saw and seal all new to existing concrete joints on Quorum Dr.

- Supply revised “As Built” plans to reflect changes to water line and fire hydrant at east side of building.

- Complete headwall construction for 12’ roof drain outlet at detention area.

- Clean/flush out storm drains.

- Lower fire hydrant at north side of building to grade.

- Center and straighten valve stack for hydrant valve at north side of building.

- Remove and replace main valve cover, and verify stack is straight and centered for valve at north side of building.

Page Two

June 5, 1998

- Provide touchpads and reader (from manufacturer) for water meters in vaults at north side of building.

- Install brass or stainless steel plugs in all DCVA test cocks.

- Grout edge of fire meter vault.

- Center and straighten fire service valve stack.

- Adjust sanitary sewer cleanout pipe and install 6” plug.

Upon receipt of your return letter, I will sign off  for a temporary Certificate of Occupancy, and upon completion of the above list, I can approve the full C.O.  Thank you for your cooperation and attention to these matters.

Sincerely,

Dave Wilde

Public Works Inspector

Town of Addison, Public Works Department

cc:	John Baumgartner

Keith Thompson

Michael Murphy

Lynn Chandler