DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN: Wade Geistweidt					REPORT DATE:

WEATHER:  Cool & Clear with Light S Wind				REPOR	T NO.:

TIME ARRIVED:  8:00 AM						TEST DATE:  1-6-11

TIME DEPARTED:  5:15 PM

PROGRESS REPORT:

Wade Geistweidt with Kleinfelder continued observation of the Vitruvian Park Phase 1D project for the Town of Addison.  Austin Bridge and Roads crews are foreman by George, Arturo Gonzalez and Derek Dodson.  These crews consist of 15 people, 7 pieces of equipment, and numerous hand and power tools.  Austin crew continued working on the Bella Lane & Ponte Ave Bridges today.  The first crew continued to work on PMD and overhang on the Ponte Ave Bridge. The second crew continued working on the column cap for bent # 2 of the Bella Lane Bridge. This work included building the form and setting the reinforcing steel for this location.  Kleinfelder also attended the weekly progress meeting to discuss the possible engineering solutions for the select fill on the Ponte Bridge Abutments.  Kleinfelder purposed that the triaxial test on the select fill be examined and give design parameters to Halff and Associates to check their design against.  This work is to be completed by Maxwell with Geotel.  Kleinfelder will also provide Halff with these design parameters.  Austin Bridge and Road is actively looking for another source to have tested and qualified.   Derek Dodson delivered a small sample to Kleinfelder today to begin PI and -200 testing on.  Derek will have a larger sample to Kleinfelder tomorrow to begin proctor and triaxial testing.  This test will be performed in case the original material still does not qualify after the engineers design parameters.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT