DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN: Wade Geistweidt							REPORT DATE:

WEATHER: Clear becoming Cloudy with light drizzle					REPOR	T NO.:

TIME ARRIVED: 8:15 AM 								TEST DATE:  11-15-10

TIME DEPARTED:  5:30 PM

PROGRESS REPORT:

Wade Geistweidt with Kleinfelder continued observation of the Vitruvian Park Phase 1D project for the Town of Addison.  Austin Bridge and Road crew is foreman by Derek Dodson and Arturo Gonzalez.  This crew consists of 6 people, 4 pieces of equipment, and numerous hand and power tools.  Austin’s crew discovered a problem with the reinforcing steel for the cantilever wall section on Abutment # 1 over the weekend.  Austin has stopped working on Abutment # 1 until the issue is resolved.  Austin did begin to set wall forms for the South wing wall on Abutment # 2 for the Ponte Bridge.  The reinforcing steel has already been placed for the remaining support and wing walls for this abutment.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT