DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN: Wade Geistweidt							REPORT DATE:

WEATHER: Clear with moderate North wind						REPOR	T NO.:

TIME ARRIVED: 8:15 AM 								TEST DATE:  11-29-10

TIME DEPARTED:  5:30 PM

PROGRESS REPORT:

Wade Geistweidt with Kleinfelder continued observation of the Vitruvian Park Phase 1D project for the Town of Addison.  Austin Bridge and Road crew is foreman by Derek Dodson and Arturo Gonzalez.  This crew consists of 15 people, 4 pieces of equipment, and numerous hand and power tools.  Austin’s crew has completed the South wing wall on Abutment # 2 and had planned to place concrete at 2 PM today for the North support wall of Abutment # 2 on the Ponte Bridge.  This placement was canceled when Jonathan McCulley rejected the reinforcing steel in this support wall.  Austin’s crew then continued setting the wall forms on the North wing wall of Abutment # 2 on the Ponte Bridge.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT