DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN: Wade Geistweidt							REPORT DATE:

WEATHER: Clear with moderate North wind						REPOR	T NO.:

TIME ARRIVED: 8:15 AM 								TEST DATE:  12-9-10

TIME DEPARTED: 5:00 PM

PROGRESS REPORT:

Wade Geistweidt with Kleinfelder continued observation of the Vitruvian Park Phase 1D project for the Town of Addison.  Austin Bridge and Road crew is foreman by Derek Dodson and Arturo Gonzalez.  This crew consists of 15 people, 4 pieces of equipment, and numerous hand and power tools.  Austin’s crew continued to place the granular backfill between the wing and support walls on Abutment # 1 for the Ponte Bridge.  This crew was able to place and test four lift of granular fill material today.  This crew continued to set forms and reinforcing steel for the stem wall cap on Abutment # 2.Austin also had a crew working on the Bella Lane Bridge.  This crew wrecked the forms from the columns on bent # 3 of the Bella Lane Bridge. These forms were then placed on the columns on bent # 2 of the Bella Lane Bridge. Kleinfelder performed 6 nuclear field density tests on the backfill.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT