DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN: Wade Geistweidt					REPORT DATE:

WEATHER: Clear with light wind					REPOR	T NO.:

TIME ARRIVED:  8:15 AM						TEST DATE:  2-15-11

TIME DEPARTED:  5:00 PM

PROGRESS REPORT:

Wade Geistweidt with Kleinfelder continued observation of the Vitruvian Park Phase 1D project for the Town of Addison.  Austin Bridge and Roads crews are foreman by George, Arturo Gonzales, and Derek Dodson.  These crews consist of 15 people, 7 pieces of equipment, and numerous hand and power tools.  Austin’s first crew continued working to install the remainder of the carrier pipes under the approach slabs for the Ponte Bridge.  They also began to wreck forms on the Ponte Bridge deck.    Austin’s second crew continued to work on Abutment # 1 for the Bella Lane Bridge.  This work included setting forms and reinforcing steel.  This crew plans to place about 120 cubic yards for this Abutment on February 16, 2011 beginning at 8 AM.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT