DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN: Wade Geistweidt					REPORT DATE:

WEATHER: Clear with light wind					REPOR	T NO.:

TIME ARRIVED:  8:15 AM						TEST DATE:  2-17-11

TIME DEPARTED:  5:00 PM

PROGRESS REPORT:

Wade Geistweidt with Kleinfelder continued observation of the Vitruvian Park Phase 1D project for the Town of Addison.  Austin Bridge and Roads crews are foreman by George, Arturo Gonzales, and Derek Dodson.  These crews consist of 15 people, 7 pieces of equipment, and numerous hand and power tools.  Austin’s first crew continued working to install the remainder of the carrier pipes under the approach slabs for the Ponte Bridge.  This crew also unloaded the remainder of the steel arches for the Ponte Bridge.      Austin’s second crew began working on the rip rap sections under the Bella Lane Bridge.  This was work for the crew until abutment # 1 has cured for 4 days and forms can be removed.  Kleinfelder also attended the weekly progress meeting today.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT