DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN: Wade Geistweidt					REPORT DATE:

WEATHER: Clear with light wind					REPOR	T NO.:

TIME ARRIVED:  8:15 AM						TEST DATE:  2-21-11

TIME DEPARTED:  5:00 PM

PROGRESS REPORT:

Wade Geistweidt with Kleinfelder continued observation of the Vitruvian Park Phase 1D project for the Town of Addison.  Austin Bridge and Roads crews are foreman by George, Arturo Gonzales, and Derek Dodson.  These crews consist of 15 people, 7 pieces of equipment, and numerous hand and power tools.  Austin’s first crew continued working to install the remainder of the carrier pipes under the approach slabs for the Ponte Bridge.  This crew also began to remove the necessary wood forms from around the arch support.  This was done so Henry and Pat Erwin could weld the wear plates to each of the arch supports.  The Erwin’s were able to weld three of the four wear plates to each of the arch supports on abutment # 1 of the Ponte Bridge.  The Erwin’s were using 3/32” 7018 welding rods to install these wear plates. The fourth wear plate will have to have an engineering fix provided by Austin or Halff and Associates.  Austin’s second crew continued working on the rip rap sections under the Bella Lane Bridge.  This crew also placed 10 cubic yards for the back wall on abutment # 4 for the Bella Lane Bridge.  Kleinfelder cast one set of 5 4X8 cylinders for this concrete placement today.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT