DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN: Wade Geistweidt					REPORT DATE:

WEATHER: Clear with strong South wind				REPOR	T NO.:

TIME ARRIVED:  8:15 AM						TEST DATE:  3-21-11

TIME DEPARTED:  7:00 PM

PROGRESS REPORT:

Wade Geistweidt with Kleinfelder continued observation of the Vitruvian Park Phase 1D project for the Town of Addison.  Austin Bridge and Road crews are foreman by Arturo Gonzales, George, Juan Salazar and Derek Dodson. These crews consist of 20 people, 7 pieces of equipment, and numerous hand and power tools.  Austin first crew placed 5 cubic yards for the remaining T401 rail on the North bound side of the Ponte Bridge near station 25+50.  This crew also continued setting forms for the sidewalks and began lay out of the hand rail on the North bound side of the Ponte Bridge.  Austin’s second crew continued select fill placement on the North side of Abutment # 1.  Austin was able to place 3 lifts of fill at this location today.  Austin’s third crew placed about 10 cubic yards for the remaining retaining wall footing at the SE corner of abutment # 4 of the Bella Lane Bridge. Austin’s welding subcontractor Erwin Iron Works continued welding the bottom wear plates on the arches of abutment #1 & 2 at the Ponte Bridge.  Kleinfelder cast 1 set of 5 4X8 cylinders, and performed 3 nuclear density tests today.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT