DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN: Wade Geistweidt					REPORT DATE:

WEATHER: Clear with strong South wind				REPOR	T NO.:

TIME ARRIVED:  8:15 AM						TEST DATE:  3-24-11

TIME DEPARTED:  6:00 PM

PROGRESS REPORT:

Wade Geistweidt with Kleinfelder continued observation of the Vitruvian Park Phase 1D project for the Town of Addison.  Austin Bridge and Road crews are foreman by Arturo Gonzales, George, Juan Salazar and Derek Dodson. These crews consist of 20 people, 7 pieces of equipment, and numerous hand and power tools.  Austin first crew continued setting forms for the wing wall caps and continued lay out of the hand rail on the North bound side of the Ponte Bridge.  Austin performed some adjustments to the handrail under Halff and Associates direction.  Austin’s second crew continued select fill placement on the North side of Abutment # 1.  Austin was able to place 3 lifts of fill at this location today.  This crew also worked to layout the bridge arches today. Austin’s third crew began setting forms for the retaining wall at the SE edge of abutment # 4 for the Bella Lane Bridge. Austin also had Gauntt Electric working on this project today.  Gauntt was installing electrical equipment on the Ponte Bridge.  Kleinfelder observed one of Gauntt's electricians performing this work off the edge of the bridge without tying off.  Kleinfelder reported this to Arturo Gonzales of Austin Bridge and Road.  Kleinfelder also spoke with Rodney of Gauntt Electric about the issue.  Rodney informed Kleinfelder that he would speak with his electrician about the issue.  Kleinfelder performed 3 nuclear density tests today.  Kleinfelder also attended the weekly progress meeting where Austin informed the group of there plans for the next week.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT