DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN: Wade Geistweidt					REPORT DATE:

WEATHER: Cloudy with strong South wind				REPOR	T NO.:

TIME ARRIVED:  8:10 AM						TEST DATE:  3-7-11

TIME DEPARTED:  5:30 PM

PROGRESS REPORT:

Wade Geistweidt with Kleinfelder continued observation of the Vitruvian Park Phase 1D project for the Town of Addison.  Austin Bridge and Roads crews are foreman by Arturo Gonzales, George, and Derek Dodson.  These crews consist of 12 people, 7 pieces of equipment, and numerous hand and power tools.  Austin’s first crew finished setting forms and reinforcing steel for the T401 rails on the west side of the Ponte Bridge.  Jonathan McCulley with Halff and Associates performed the reinforcing steel inspection. Austin then placed 3.5 cubic yards for the T401 rail.  Austin’s second crew continued to set forms, overhangs, and carrier pipes for the Bella Lane Bridge.  Austin’s welding subcontractor Erwin Iron Works continued working on the steel arches for the Ponte Bridge.  This work included all three fulltime welders and a new part-time welder working on weld out of the side plates.  Kleinfelder received comments back from Robert Boswell Kleinfelders lead CWI about the welding procedures submitted by Austin Bridge and Road.  This procedure does not match the specifications for the project.  Austin will have to submit another procedure in accordance with the codes and specifications of the project.  These comments were uploaded to project mates for reference.  Kleinfelder cast one set of 5 4X8 cylinders for the placement today.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT