DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN: Wade Geistweidt					REPORT DATE:

WEATHER: Clear with light wind					REPOR	T NO.:

TIME ARRIVED:  8:15 AM						TEST DATE:  4-14-11

TIME DEPARTED:  5:30 PM

PROGRESS REPORT:

Wade Geistweidt with Kleinfelder continued observation of the Vitruvian Park Phase 1D project for the Town of Addison.  Austin Bridge and Road crews are foreman by Arturo Gonzales, George, Juan Salazar and Derek Dodson. These crews consist of 15 people, 7 pieces of equipment, and numerous hand and power tools.  Austin first crew completed preparations of the sidewalk drain on the South bound lanes of the Ponte Bridge.  This crew placed about 3 cubic yards of concrete for the section of sidewalk under the handrails   This crew also had rod busters onsite to set the reinforcing steel for the approach slab on abutment # 2 of the Ponte Bridge.  Austin’s second and third crew set the arches on the Bella Lane Bridge today.  These arches were set and in place by 11 AM.  This crew also placed the wing wall caps on abutment # 1 for the Bella Lane Bridge.  Austin’s welding contractor Erwin Steel Works was onsite today.  This crew consisted of 2 welders and numerous hand and power tools.  The welders installed bracing for the arches to be lifted without damaging them.  After the arches were set in place both welders began welding the lower slide plates on.   Kleinfelder cast one set of 5 4X8 cylinders today.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT