DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN: Wade Geistweidt					REPORT DATE:

WEATHER: Cloudy with chance for rain					REPOR	T NO.:

TIME ARRIVED:  8:15 AM						TEST DATE:  4-19-11

TIME DEPARTED:  5:00 PM

PROGRESS REPORT:

Wade Geistweidt and David Hernandez with Kleinfelder continued observation of the Vitruvian Park Phase 1D project for the Town of Addison.  Austin Bridge and Road crews are foreman by Arturo Gonzales, George, and Derek Dodson. These crews consist of 10 people, 7 pieces of equipment, and numerous hand and power tools.  Austin first crew placed 24 cubic yards of concrete for the South bound sidewalk on the Ponte Bridge.  This placement was between stations 24+38 to 25+65.  Austin’s second completed layout of the support slab for abutment # 4 of the Bella Lane Bridge.  This crew placed 12 cubic yards for this support slab today.  Erwin Steel Works had two welders onsite to continue fitting and welding the bottom slide plates to the abutment embed.  Kleinfelder cast two sets of 5 4X8 cylinders for the sidewalk placement, and the support slab today.  David Hernandez with Kleinfelder spoke with the painting crew from Scott Deer Painting.  This conversation was about what products they were to use and how they plan to prepare the surfaces for painting.  While speaking with this crew David was able to find out that this crew planned to apply the Sherwin Williams products that had been rejected.  Austin was still dealing with submitting surface preparation plans and product data sheets from Carboline.  David Hernandez was needed on another site and left for the day.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT