DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN: Wade Geistweidt					REPORT DATE:

WEATHER: Cloudy with chance for rain					REPOR	T NO.:

TIME ARRIVED:  8:15 AM						TEST DATE:  4-26-11

TIME DEPARTED:  5:45 PM

PROGRESS REPORT:

Wade Geistweidt and David Hernandez with Kleinfelder continued observation of the Vitruvian Park Phase 1D project for the Town of Addison.  Austin Bridge and Road crews are foreman by Arturo Gonzales, George, and Derek Dodson. These crews consist of 10 people, 7 pieces of equipment, and numerous hand and power tools.  Austin first and second crews worked together today on the Bella Lane and Ponte Ave Bridges.  This work included finishing the reinforcing steel work on the T 401 rail end caps at both bridges.  These crews place about 4cubic yards of concrete for the T 401 rail end caps.  Austin also had there painting contractor Scott Derr onsite to clean the weld seams on the left arch for the Ponte Bridge.  This crew was able to get the left arch weld seams cleaned and painted with primer today.  Scott Derr’s superintendent Don Gandy informed Kleinfelder that they wanted to begin applying the intermediate epoxy paint coat tomorrow.  This crew plans to power wash the arch again and begin painting after it has dried.  Kleinfelder made an observation today while Austin’s crew was beginning to form the sidewalk on the approach slab for Abutment # 2.  Kleinfelder notice that when the curb line for the brick pavers is installed this will create an area for water to collect.  Austin and UDR are aware of the issue and Austin is developing a solution for this problem.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT