DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN: Wade Geistweidt					REPORT DATE:

WEATHER: Clear with moderate South wind				REPOR	T NO.:

TIME ARRIVED:  8:15 AM						TEST DATE:  4-5-11

TIME DEPARTED:  4:00 PM

PROGRESS REPORT:

Wade Geistweidt with Kleinfelder continued observation of the Vitruvian Park Phase 1D project for the Town of Addison.  Austin Bridge and Road crews are foreman by Arturo Gonzales, George, Juan Salazar and Derek Dodson. These crews consist of 20 people, 7 pieces of equipment, and numerous hand and power tools.  Austin first crew continued welding the handrails to the embed plates on the Ponte Ave Bridge.  This crew also prepared the sub grade for the sleeper slab and the approach slab at abutment # 1 of the Ponte Bridge.  Austin’s second crew continued forming the T401 rail along the N bound lanes of the Bella Lane Bridge.  Austin’s third crew continued to set forms for the abutment wall caps on bents 1 and 4 of the Bella Lane Bridge.  Austin Bridge and Road welding contractor Erwin Steel Works was onsite today.  This crew consists of 3 welders.  They continued to weld out the side plates for each of the field splices.  Kleinfelder spoke with Henry Erwin of Erwin Steel Works today about schedule and when they plan to be ready for ultra sonic testing.  Mr. Erwin plans to be ready for UT testing on Friday April 8, 2011.  Kleinfelder performed two nuclear density tests for the sub grade prep Austin first crew performed.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT