DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN: Wade Geistweidt					REPORT DATE:

WEATHER: Clear with moderate South wind				REPOR	T NO.:

TIME ARRIVED:  8:15 AM						TEST DATE:  4-6-11

TIME DEPARTED:  5:30 PM

PROGRESS REPORT:

Wade Geistweidt with Kleinfelder continued observation of the Vitruvian Park Phase 1D project for the Town of Addison.  Austin Bridge and Road crews are foreman by Arturo Gonzales, George, Juan Salazar and Derek Dodson. These crews consist of 20 people, 7 pieces of equipment, and numerous hand and power tools.  Austin first crew continued working to set the forms and reinforcing steel in place for the sleeper slab.  This crew placed 12 cubic yards of concrete at 3:30 PM today.   Austin’s second crew continued forming the T401 rail on the S bound lanes of the Bella Lane Bridge.  This crew, and the third crew placed a total of 7 cubic yards of concrete for the T401 rail and the abutment wall caps on the Bella Lane Bridge. Austin’s third crew placed 2 of the 7 yards mentioned above on the abutment 4 cap.  Austin Bridge and Road welding contractor Erwin Steel Works was onsite today.  This crew consists of 3 welders.  This crew continued welding out the side plates at each of the field splices on the arches for Bella Lane.  Kleinfelder cast two sets of 5 4X8 cylinders for the concrete placements today.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT