DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN: Wade Geistweidt					REPORT DATE:

WEATHER: Clear with moderate South wind				REPOR	T NO.:

TIME ARRIVED:  8:15 AM						TEST DATE:  4-7-11

TIME DEPARTED:  5:30 PM

PROGRESS REPORT:

Wade Geistweidt with Kleinfelder continued observation of the Vitruvian Park Phase 1D project for the Town of Addison.  Austin Bridge and Road crews are foreman by Arturo Gonzales, George, Juan Salazar and Derek Dodson. These crews consist of 20 people, 7 pieces of equipment, and numerous hand and power tools.  Austin first crew continued working to set the forms and reinforcing steel for the approach slab at abutment # 1 of the Ponte Bridge.  This crew plans to place about 90 cubic yards of concrete at 10 AM on April 8, 2011.   Austin’s second crew continued forming the T401 rail on the S bound lanes of the Bella Lane Bridge.  This crew and the third crew placed a total of 6 cubic yards of concrete for the T401 rail and the retaining wall cap on the Bella Lane Bridge. Austin’s third crew placed 2 of the 6 yards mentioned above on the retaining wall cap.  Austin Bridge and Road welding contractor Erwin Steel Works was onsite today.  This crew consists of 3 welders.  This crew continued welding out the side plates at each of the field splices on the arches for Bella Lane.  This crew planned to complete this task today and was working to make adjustments to the lifting eyes and get them tacked in place today.  Kleinfelder cast one set of 5 4X8 cylinders for the concrete placements today.  Kleinfelder also performed a reinforcing steel inspection for the approach slab at abutment # 1 of the Ponte Bridge.  Kleinfelder also attended the weekly progress meeting today.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT