DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN: Wade Geistweidt					REPORT DATE:

WEATHER: Mostly Cloudy with North wind				REPOR	T NO.:

TIME ARRIVED:  8:15 AM						TEST DATE:  5-20-11

TIME DEPARTED:  3:30 PM

PROGRESS REPORT:

Wade Geistweidt with Kleinfelder continued observation of the Vitruvian Park Phase 1D project for the Town of Addison.  Austin Bridge and Road crews are foreman by Arturo Gonzales, George, and Derek Dodson. These crews consist of 10 people, 7 pieces of equipment, and numerous hand and power tools.  Austin first crew continued working to level out the weld seams on the arches of the Ponte Bridge.  This crew also continued working on punch list items for the Ponte Ave Bridge.  Austin second crew also continued working to level out the weld seams on the arches of the Bella Lane Bridge.  This crew also continued working on punch list items for the Bella Lane Bridge today.  Austin’s crew work onsite was limited do to the heavy rain showers that were passing through thru out the day.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT