DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN: Wade Geistweidt					REPORT DATE:

WEATHER: Cloudy with strong South wind and HOT			REPOR	T NO.:

TIME ARRIVED:  8:15 AM						TEST DATE:  6-13-11

TIME DEPARTED:  5:10 PM

PROGRESS REPORT:

Wade Geistweidt with Kleinfelder continued observation of the Vitruvian Park Phase 1D project for the Town of Addison.  Austin Bridge and Road crews are foreman by George, and Andrew Harper. These crews consist of 4 people, 2 pieces of equipment, and numerous hand and power tools.  Austin crew worked to clean up the concrete saw spray on the curb lines at the Ponte Bridge.  This crew also began laying out saw cuts for repairs on the Bella Lane Bridge deck and approach slabs.  Mr. Clay Barnett with the Town of Addison was onsite to look at the repairs on the Ponte Ave Bridge.  Mr. Barnett stated that the repairs were ok, but he also wanted to get a second opinion from Ms. Lea Dunn the Assistant City Manager.   The painting crew from Scott Derr Painting arrived onsite to continue sanding the right arch of the Ponte Bridge at 10:30 AM.  This crew worked through out the day to sand the ruff paint to a smooth surface. There was no painting performed today on either of the bridges.  Kleinfelder asked Louis with Scott Derr Painting when they planned to start painting again.  Louis stated that they would have another crew onsite tomorrow to begin cleaning the Bella Lane arches and apply the top coat at this location.  Louis plans to continue sanding and then begin applying the intermediate coat to both arches at the Ponte Bridge.  Kleinfelder plans to have David Hernandez onsite to perform painting inspections thru out the day.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT