DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN: Wade Geistweidt					REPORT DATE:

WEATHER: Cloudy with moderate South wind and HOT			REPOR	T NO.:

TIME ARRIVED:  8:15 AM						TEST DATE:  6-15-11

TIME DEPARTED:  5:15 PM

PROGRESS REPORT:

Wade Geistweidt with Kleinfelder continued observation of the Vitruvian Park Phase 1D project for the Town of Addison.  Austin Bridge and Road crews are foreman by George, and Andrew Harper. These crews consist of 4 people, 2 pieces of equipment, and numerous hand and power tools.  Austin crew placed 3 cubic yards of concrete for the bird bath drainage repairs on the approach slab at abutment # 4 of the Bella Lane Bridge.   The painting crew from Scott Derr Painting arrived onsite at 8:00 AM.  This crew was ready to power wash the Bella Lane arches so the final top coat could be applied.  This was stopped due to strong to moderate South winds today.  The fear was the over spray paint getting airborne and damaging other property and structures.  The painters did power wash the arches at the Ponte Bridge to get them ready to apply the intermediate coat.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT