DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN:	Wade Geistweidt & Paul Kidd			REPORT DATE:

WEATHER:  Clear & Hot with light variable			REPORT NO.:

TIME ARRIVED:  7:00 AM 					TEST DATE:  8-13-10

TIME DEPARTED:  4:30 PM

PROGRESS REPORT:

Wade Geistweidt and Paul Kidd of Kleinfelder continued observation of the Vitruvian Park Phase 1D project for The Town of Addison.  Austin Bridge and Road had W W Drilling onsite again today to continue drilling piers for abutment # 1 and 2 for the Ponte Bridge. Austin Bridge and Road foreman is Derek Dodson. Austin’s crew consisted of 1 person and 3 piece of equipment.  W W Drillings crew is foreman by Chuck Simmons.  This crew consists of 3 people and 1 piece of equipment.  WW Drilling was able to complete 2 drilled shafts today.  There was one shaft completed on abutment # 2 and a second completed on abutment # 1.  This brings the total complete to 7 of 32.  Kleinfelder recorded the data from each of the completed shafts and cast one set of 4X8 cylinders today.  Kleinfelder also picked up samples of the hard rock formation that the driller is encountering.  These samples were taken to the DFW office to be examined by Don James.  Mr. James stated that the mineral found in the rock would not be harmful to concrete being in contact with it.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT