DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN:	Wade Geistweidt & Paul Kidd			REPORT DATE:

WEATHER:  Clear & Hot with light variable			REPORT NO.:

TIME ARRIVED:  7:00 AM 					TEST DATE:  8-16-10

TIME DEPARTED:  4:30 PM

PROGRESS REPORT:

Wade Geistweidt and Paul Kidd of Kleinfelder continued observation of the Vitruvian Park Phase 1D project for The Town of Addison.  Austin Bridge and Road had W W Drilling onsite again today to continue drilling piers for abutment # 1 for the Ponte Bridge. Austin Bridge and Road foreman are Derek Dodson and Arturo Gonzalez. Austin’s crew consisted of 6 people and 3 piece of equipment.  Austin’s crew mobilized onsite to begin forming the abutment and wing walls for abutments # 1& 2.  W W Drillings crew is foreman by Chuck Simmons.  This crew consists of 3 people and 1 piece of equipment.  WW Drilling was able to complete 2 48” drilled shafts today.  These shafts were both completed on abutment # 1.  This brings the total complete to 11 of 32.  Kleinfelder recorded the data from each of the completed shafts and cast one set of 5 4X8 cylinders today.  Kleinfelder return the rock sample to Kleinfelder DFW office to have sulfate testing performed.  This was done as a confirmation check to make sure there were no sulfates to affect the concrete in the piers.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT