DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN:	Wade Geistweidt & Paul Kidd			REPORT DATE:

WEATHER:  Clear & Hot with light variable			REPORT NO.:

TIME ARRIVED:  7:00 AM 					TEST DATE:  8-20-10

TIME DEPARTED:  5:00 PM

PROGRESS REPORT:

Wade Geistweidt and Paul Kidd of Kleinfelder continued observation of the Vitruvian Park Phase 1D project for The Town of Addison.  Austin Bridge and Road had W W Drilling onsite again today to continue drilling piers for abutment # 1 for the Ponte Bridge. Austin Bridge and Road foreman are Derek Dodson and Arturo Gonzalez. Austin’s crew consisted of 7 people and 3 piece of equipment.  W W Drillings crew is foreman by Chuck Simmons.  This crew consists of 3 people and 1 piece of equipment.  WW Drilling was able to complete 1 48” & 1 54” drilled shafts today.  WW drilling decided to start a third shaft today however this shaft only had the steel casing set today.  WW Drilling will finish this shaft on Saturday August 21, 2010.  These shafts were both completed on abutment # 1.  This brings the total complete to 19 of 32 on both abutments # 1 & 2.  Kleinfelder recorded the data from each of the completed shafts and cast one set of 5 4X8 cylinders today.  Austin Bridge and Road also receive a load of reinforcing steel today.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT