DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN:	Wade Geistweidt & Paul Kidd				REPORT DATE:

WEATHER:  Mostly Clear & Hot with light variable Winds		REPORT NO.:

TIME ARRIVED:  7:00 AM 						TEST DATE:  8-25-10

TIME DEPARTED:  5:00 PM

PROGRESS REPORT:

Wade Geistweidt and Paul Kidd of Kleinfelder continued observation of the Vitruvian Park Phase 1D project for The Town of Addison.  Austin Bridge and Road had W W Drilling onsite again today to continue drilling piers for abutment # 2 for the Ponte Bridge. Austin Bridge and Roads foreman are Derek Dodson and Arturo Gonzalez. Austin’s crew consisted of 7 people and 3 piece of equipment.  Austin’s crew continued setting forms on the Abutment # 1 piers.  Austin also had a rod busting crew onsite building reinforcing steel cages for the footings on abutment # 1.  WW Drillings crew is foreman by Chuck Simmons.  This crew consists of 3 people and 1 piece of equipment.  WW Drilling was able to complete 1 54” and 1 48” drilled shafts today.  Both of the piers drilled today were completed on abutment # 2.  This brings the total complete to 26 of 32 on both abutments # 1 & 2.  Kleinfelder recorded the data from each of the completed shafts and cast one set of 5 4X8 cylinders today.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT