DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN:	Wade Geistweidt & Paul Kidd				REPORT DATE:

WEATHER:  Mostly Clear & Hot with light variable Winds		REPORT NO.:

TIME ARRIVED:  7:00 AM 						TEST DATE:  8-26-10

TIME DEPARTED:  5:00 PM

PROGRESS REPORT:

Wade Geistweidt and Paul Kidd of Kleinfelder continued observation of the Vitruvian Park Phase 1D project for The Town of Addison.  Austin Bridge and Road had W W Drilling onsite again today to continue drilling piers for abutment # 2 for the Ponte Bridge. Austin Bridge and Roads foreman are Derek Dodson and Arturo Gonzalez. Austin’s crew consisted of 7 people and 3 piece of equipment.  Austin’s crew placed 24 cubic yards of concrete for the east wing wall of Abutment # 1.  Austin’s crew also continued setting forms on the Abutment # 1 piers.  Austin had a rod busting crew onsite building reinforcing steel cages for the footings on abutment # 1.  Jonathan MCCulley and Major Jones with Halff Associates were also on site to perform a reinforcing steel inspection for the east wing wall of abutment # 1.  Mr. MCCulley and Mr. Jones were both satisfied with the work Austin had done with the reinforcing steel on this footer.  WW Drillings crew is foreman by Chuck Simmons.  This crew consists of 3 people and 1 piece of equipment.  WW Drilling was able to complete 1 54” and 1 48” drilled shafts today.  Both of the piers drilled today were completed on abutment # 2.  This brings the total complete to 28 of 32 on both abutments # 1 & 2.  Kleinfelder recorded the data from each of the completed shafts and cast two set of 5 4X8 cylinders today.  Kleinfelder also attended the weekly progress meeting for this project today.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT