DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN:	Wade Geistweidt & Paul Kidd				REPORT DATE:

WEATHER:  Partly Cloudy with Light variable winds	 		REPORT NO.:

TIME ARRIVED:  7:00 AM 						TEST DATE:  9-13-10

TIME DEPARTED:  5:00 PM

PROGRESS REPORT:

Wade Geistweidt and Paul Kidd of Kleinfelder continued observation of the Vitruvian Park Phase 1D project for The Town of Addison.  Austin Bridge and Road had W W Drilling onsite again today to continue drilling piers on Abutment # 1 and Bent # 2 for the Bella Bridge.  Austin Bridge and Roads foreman are Derek Dodson and Arturo Gonzalez. Austin’s crew consisted of 14 people and 3 piece of equipment.  Austin’s crew continued placement of reinforcing steel and setting forms for the abutment # 2 footings on the Ponte Bridge.  WW Drillings crew is foreman by Chuck Simmons.  This crew consists of 4 people and 1 piece of equipment.  WW Drilling was able to complete 1 48”, 2 30”, and 1 42”, drilled shafts on abutment # 1 and bent # 2 for the Bella Lane Bridge.  This brings total complete to 32 of 32 on Ponte Bridge, 16 of 24 on Bella Lane Bridge and 2 of 4 at the pedestrian Bridge.  Kleinfelder recorded the data from each of the completed shafts and cast one set of 5 4X8 cylinders today.  Austin Bridge and Road had ONCOR Electric Delivery shut down the power lines next to abutment # 1 and bent # 2 today.  The four piers completed were near this location.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT