DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN:	Wade Geistweidt & Paul Kidd				REPORT DATE:

WEATHER:  Partly Cloudy with Light variable winds	 		REPORT NO.:

TIME ARRIVED:  7:00 AM 						TEST DATE:  9-16-10

TIME DEPARTED:  3:00 PM

PROGRESS REPORT:

Wade Geistweidt and Paul Kidd of Kleinfelder continued observation of the Vitruvian Park Phase 1D project for The Town of Addison.  Austin Bridge and Road had W W Drilling onsite again today to continue drilling piers on Abutment # 2 for the pedestrian bridge.  Austin Bridge and Roads foreman are Derek Dodson and Arturo Gonzalez. Austin’s crew consisted of 14 people and 3 piece of equipment.  Austin’s crew finished setting forms for the south support wall on abutment #1 for the Ponte Bridge.  Austin also finished setting forms on the creek wall on bent #3 at the Bella Lane Bridge.  WW Drillings crew is foreman by Chuck Simmons.  This crew consists of 4 people and 1 piece of equipment.  WW Drilling was able to complete 2 24” drilled shafts on abutment #2 for the pedestrian bridge.  This brings the total complete to 32 of 32 on the Ponte Bridge, 24 of 24 on the Bella Lane Bridge and 4 of 4 at the pedestrian Bridge.  Kleinfelder recorded the data from each of the completed shafts and cast one set of 5 4X8 cylinders today.  Halff and Associates performed the reinforcing steel inspections for the abutment #1 support wall and the creek wall on bent #3 on the Bella Lane Bridge.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT