DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN:	Wade Geistweidt					REPORT DATE:

WEATHER:  	Partly Cloudy with light Variable winds			REPOR	T NO.:

TIME ARRIVED:  8:15 AM						TEST DATE:  9-17-10

TIME DEPARTED:  5:30 PM

PROGRESS REPORT:

Wade Geistweidt with Kleinfelder continued observation of the Vitruvian Park Phase 1D project for the Town of Addison.  Austin Bridge and Road crews are foreman by Derek Dodson and Arturo Gonzalez.  These crews consist of 15 people, 3 pieces of equipment and numerous power tools.  The first crew placed concrete for the south support wall on Abutment #1 of the Ponte Bridge.  They also began to wreck forms on the footing of Abutment # 2 and prepared to reset them on Saturday September 18.  This plan is so concrete can be placed early next week on these Abutment footings.  The second crew placed concrete for the creek edge wall on Bent # 3 of the Bella Lane Bridge.  Kleinfelder cast two sets of 5 4X8 cylinders for today placements.  Halff and Associates performed the reinforcing steel inspections for each of the bridge structures today.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT