DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN:	Wade Geistweidt					REPORT DATE:

WEATHER:  	Partly Cloudy with light Variable winds			REPOR	T NO.:

TIME ARRIVED:  8:15 AM						TEST DATE:  9-22-10

TIME DEPARTED:  5:15 PM

PROGRESS REPORT:

Wade Geistweidt with Kleinfelder continued observation of the Vitruvian Park Phase 1D project for the Town of Addison.  Austin Bridge and Road crews are foreman by Derek Dodson and Arturo Gonzalez.  These crews consist of 15 people, 3 pieces of equipment and numerous hand and power tools.  The first crew continued working on the footers for Abutment # 2.  This crew was able to finish setting the forms and reinforcing steel on the remaining footer.  Austin plans to place concrete on this footer on Thursday September 23 at 10 AM.  The second crew placed 35 cubic yards of concrete for the creek wall on bent # 2 on the Bella Lane Bridge. This crew will be wrecking forms at this location tomorrow.  Halff and Associates completed the reinforcing steel inspections for Abutment # 2 on the Ponte Ave Bridge and the creek wall on bent #2 for the Bella Lane Bridge.  Kleinfelder cast one set of 5 4X8 cylinders for the concrete placement today.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT