DAILY REPORT SUMMARY

TO:	Town of Addison						PROJECT:  Vitruvian Park - Addison, TX

16801 Westgrove Drive								Infrastructure Phase 1D

Addison, TX  75001-5190					PROJECT NO.: 99526 – 5

TECHNICIAN:	Wade Geistweidt					REPORT DATE:

WEATHER:  	Partly Cloudy with light Variable winds			REPOR	T NO.:

TIME ARRIVED:  8:15 AM						TEST DATE:  9-23-10

TIME DEPARTED:  5:15 PM

PROGRESS REPORT:

Wade Geistweidt with Kleinfelder continued observation of the Vitruvian Park Phase 1D project for the Town of Addison.  Austin Bridge and Road crews are foreman by Derek Dodson and Arturo Gonzalez.  These crews consist of 15 people, 3 pieces of equipment and numerous hand and power tools.  The first crew placed 54 cubic yards of concrete for the left footer on Abutment # 2 on the Ponte Bridge. The second crew wrecked the forms from the wall on Bent #2 on the Bella Lane Bridge today.  Halff and Associates completed the reinforcing steel inspections for the footer on Abutment # 2 of the Ponte Ave Bridge. Kleinfelder cast one set of 5 4X8 cylinders for the concrete placement today on Ponte.

COPIES TO:	Clay Barnett							KLEINFELDER

DRAFT