## density
Y or N
[11 empty] | Calculate Percent Proctor Density to nearest 0.1%: |  |  |  |  | y
IN-PLACE MOISTURE DENSITY TEST RESULTS
| To: | Town of Addison |  |  |  |  | Test Date: | 2010-09-28
|  | 16801 Westgrove Drive |  |  |  |  | Project No: | 99526 - 5
|  | Addison, TX 75001-5190 |  |  |  |  | Report Date: | 2026-07-29
Report No:
Project: |  | Vitruvian Park and Misc Projs |  |  |  |  | Definitions of Terms
Location: |  | Addison, TX |  |  |  |  | RQP- Rt Qtr Point |  | CL - Centerline
Field Rep: |  | Wade Geistweidt |  |  |  |  | LQP - Lt Qtr Point |  | Sta - Station
| Test | Test Location |  | Depth | Wet | Field | Dry | Proctor |  | Percent
| No. |  |  | Lift | Density | Moisture | Density | No. |  | Proctor | Proctor No.
[6 empty] | (%) | (pcf) |  |  | Density | 1 | 2 | 3 | 4 | Sum
|  | Backfill of Abutment #1 Footings | [7 empty] | #VALUE! | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #VALUE!
|  | West side of storm drain box @ station 24+00 |  | 3 | 117.18 | 30.2 | 90 | 2902 |  | 96 | 0 | 0 | 93.4 | 0 | 93.4 |  | 96.4 | 1 | 0 | 0 | 0 | 96
|  | East side of storm drain box @ station 24+25 |  | 4 | 121.6475 | 23.5 | 98.5 | 2759 |  | 101 | 0 | 97.6 | 0 | 0 | 97.6 |  | 100.9 | 1 | 0 | 0 | 0 | 101
|  | North side of storm drain box @ station 24+00 |  | 5 | 114.6728 | 25.6 | 91.3 | 2592 |  | 95 | 95.9 | 0 | 0 | 0 | 95.9 |  | 95.2 | 1 | 0 | 0 | 0 | 95
|  | South side of storm drain box @ station 24+25 |  | 5 | 115.736 | 25.8 | 92 | 2592 |  | 96 | 95.9 | 0 | 0 | 0 | 95.9 |  | 95.9 | 1 | 0 | 0 | 0 | 96
|  | 30' W of centerline at station 24+00 |  | F | 113.0808 | 27.2 | 88.9 | 2902 |  | 95 | 0 | 0 | 93.4 | 0 | 93.4 |  | 95.2 | 1 | 0 | 0 | 0 | 95
|  | 30' E of Centerline at Station 24+00 |  | F | 119.8164 | 25.2 | 95.7 | 2592 |  | 100 | 95.9 | 0 | 0 | 0 | 95.9 |  | 99.8 | 1 | 0 | 0 | 0 | 100
|  | Backfill of Abutment # 2 Footings |  |  | 0 |  |  |  |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #VALUE!
|  | 50' E of Centerline at Station 25+80 |  | 1 | 118.5046 | 23.7 | 95.8 | 2759 |  | 98 | 0 | 97.6 | 0 | 0 | 97.6 |  | 98.2 | 1 | 0 | 0 | 0 | 98
|  | 30' E of Centerline at station 25+80 |  | 1 | 120.8466 | 24.2 | 97.3 | 2759 |  | 100 | 0 | 97.6 | 0 | 0 | 97.6 |  | 99.7 | 1 | 0 | 0 | 0 | 100
|  | 50' W of Centerline at Station 25+80 |  | 1 | 119.7678 | 29.9 | 92.2 | 2902 |  | 99 | 0 | 0 | 93.4 | 0 | 93.4 |  | 98.7 | 1 | 0 | 0 | 0 | 99
[5 empty] | 0 |  |  |  |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #VALUE!
[5 empty] | 0 |  |  |  |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #VALUE!
[5 empty] | 0 |  |  |  |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #VALUE!
[5 empty] | 0 |  |  |  |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #VALUE!
[5 empty] | 0 |  |  |  |  | #VALUE! | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #VALUE!
| Proctor No: |  | Description |  |  |  | Opt. Moisture |  | Max. Density |  | Proctor No. | [8 empty] | 0 | 0
2592 |  |  | Dark Brown fat Clay |  |  |  | 25.1 |  | 95.9 | [6 empty] | 0
2759 |  |  | Dark Brown Sandy Clay |  |  |  | 23.5 |  | 97.6 | [6 empty] | 0
2902 |  |  | Dark Brown fat Clay with Sand |  |  |  | 26.4 |  | 93.4 | [6 empty] | 0
0
Specs. |  |  | Gauge No: | 32755 |  |  | Test Methods: |  | ASTM D 6938 |  |  |  | Min. | Max.
Dens. (%) |  | Min 95 | Std. Density Count: | 2420 |  |  |  |  | ASTM D 698 |  | Density Specs |  | 95
Moist. (%) |  | 0 to 4 | Std. Moist Count: | 650 | [6 empty] | Moisture Specs. |  | 0 | 4
|  |  | Trans. Depth (in.): | 6
Remarks:
| Copies: | 2- Client
KLEINFELDER
DRAFT
The results shown on this report are for the exclusive use of the client for whom they were obtained and apply only to the samples tested and/or inspected. They are not intended to be
indicative of the qualities of apparently identical products. The use of our name must receive prior written approval. Reports must be reproduced in their entirety.
2035 Central Circle, Suite 110
McKinney, TX
75069-8524
p| 972.562.4677
f| 972.542.4366
kleinfelder.com

## INFO
Do Not Change ANYTHING on this! Always SAVE AS
10/01
| Town of Addison |  | Vitruvian Park and Misc Projs
| 16801 Westgrove Drive |  | Addison, TX
Addison, TX 75001-5190
|  | Project No.: | 99526 - 5
Reports to:
2- Client
email:
fax No.:
voice No.:
project manager:
The results shown on this report are for the exclusive use of the client for whom they were obtained and apply only to the samples tested and/or inspected. They are not intended to be
indicative of the qualities of apparently identical products. The use of our name must receive prior written approval. Reports must be reproduced in their entirety.