## reinforcing steel visual obs
REINFORCING STEEL VISUAL OBSERVATIONS
| TO: | Town of Addison |  |  |  | PROJECT: | Vitruvian Park and Misc Projs
|  | 16801 Westgrove Drive |  |  |  |  | Addison, TX
|  | Addison, TX 75001-5190 |  |  |  | PROJECT NO.: | 99526 - 5
[7 empty] | REPORT DATE: | 2026-07-29
REPORT NO.:
|  |  | Technician: | Wade Geistweidt
|  |  | Observation Date: | 2011-04-29
|  |  | Item / Object Observed: | Slab | Grade Beam |  | Paving
|  |  |  | Wall | Column |  | Other__________________________
|  |  | Specific Observation Location: | NW sidewalk and brick paver base
|  |  | Referenced Drawing: | S4-03 Ponte Plan
Results:
Reinforcing steel placed in general accordance with the project drawings.
Exceptions noted and referred to contractor for correction.
Exceptions noted and referred to structural engineer.
Exceptions corrected prior to placement of concrete.
Remarks:
| COPIES TO: | 2- Client |  |  |  |  | KLEINFELDER
DRAFT
The results shown on this report are for the exclusive use of the client for whom they were obtained and apply only to the samples tested and/or inspected. They are not intended to be
indicative of the qualities of apparently identical products. The use of our name must receive prior written approval. Reports must be reproduced in their entirety.
2035 Central Circle, Suite 110
McKinney, TX
75069-8524
p| 972.562.4677
f| 972.542.4366
kleinfelder.com

## INFO
Do Not Change ANYTHING on this! Always SAVE AS
10/01
| Town of Addison |  | Vitruvian Park and Misc Projs
| 16801 Westgrove Drive |  | Addison, TX
Addison, TX 75001-5190
|  | Project No.: | 99526 - 5
Reports to:
2- Client
email:
fax No.:
voice No.:
project manager:
The results shown on this report are for the exclusive use of the client for whom they were obtained and apply only to the samples tested and/or inspected. They are not intended to be
indicative of the qualities of apparently identical products. The use of our name must receive prior written approval. Reports must be reproduced in their entirety.