## Preston - Dooley
NTP | 2018-11-27
Contract Days | 175 |  |  | Contract Amount | 1180035
Days Used | 106 |  |  | Paid To Date | 364833.25
Days Remaining | 69
|  | Contract Time Used | 57%
|  | Contract Amount Paid | 17%

## Sherlock
NTP | 2018-07-12
Contract Days | 160 |  |  | Contract Amount | 1324990
Days Used | 119 |  |  | Paid To Date | 261772.5
Days Remaining | 41
|  | Contract Time Used | 45%
|  | Contract Amount Paid | 0%