## Infinity HVAC Totals
Flowline Construction
Phase 8 Invoice Tracker |  |  |  | 1180035
-815201.75
Invoice No. | Total | Retainage (5%) | Payment
1 | 118617.5 | -5930.875 | 112686.625
2 | 265417.5 | -13270.875 | 252146.625
3
4
5
6
7
8
9
10
11
12
Total | 384035 | -19201.75 | 364833.25
384035
0

## Infinity - Invoice 1
Infinity Payment
Addison Athletic Club - HVAC Project
Invoice #1
Total | 118617.5
Retainage | -5930.875
Payment Amount | 112686.625

## Infinity - Invoice 2
Infinity Payment
Addison Athletic Club - HVAC Project
Invoice #2
Total | 265417.5
Retainage | -13270.875
Payment Amount | 252146.625