## Slide 1: Addison Athletic Club HVAC Improvements
November 13, 2018

## Slide 2: History – Athletic Club HVAC Project
August 14, 2018 – Staff presented updated cost estimate to Council
  Estimated Base bid of $1,119,293
  Estimated Additive alternate bid of $484,025
August 2018 – September 2018 – Plans and specifications were updated
September 20, 2018 – HVAC project re-bid was placed on Bidsync
October 18, 2018 – HVAC project bid closed
  Town received a total of 4 bids
Contractor | Total Base Bid | Additive Alternate Bid | Total Base w/ Alternate
Infinity Contractors International, LTD. | $913,329 | $266,706 | $1,180,035
TDI Industries | $1,103,553 | $280,245 | $1,383,798
MIINC | $1,100,566 | $374,750 | $1,475,316
308 Construction | $2,675,000 | $475,000 | $3,150,000

## Slide 3: HVAC Base Bid and Additive Alternates
Additive Alternates
  Air Handling Unit’s 1, 2, 3, 6, & 7
  Replacement of the gymnasium duct work
  Replacement of the roof mounted, air relief hood in the gymnasium
Boiler, AHU 4, and pump 10 will not be replaced in either scenario

## Slide 4: Budget Information
Available Budget | $1,004,640.00
Base Bid | $913,329.00
Add Alt Bid | $266,706.00
Subtotal | $1,180,035.00
Construction Contingency | $100,000.00
Remaining Design Payment | $20,973.63
Construction Management | $66,720.00
Project Total | $1,367,728.63
Funds Needed | $363,088.63
August 2018 Estimate
  Base bid - $1,119,293
  Alternate bid - $484,025
  Total bid - $1,603,318
Staff recommends award of base bid and additive alternate bid
  Utilize General Fund – fund balance
  Additive alternates are competitively priced
  Less overall disruption to the facility
Base bid + design + construction management - $1,001,022.63
  Can be done with current available funds

## Slide 5: HVAC Project – Next Steps
Contractor will prepare material submittals for review and approval
  Is expected to take approximately 3 weeks
Construction is expected to take 5 months from approval of the submittals
Coordinate with the Athletic Club staff
Provide communication to Athletic Club members

## Slide 6: Questions?