## Sheet1
Town of Addison
Summary of Engineering Revision Comments
Development: | Galaxy FBO |  |  | Town Project #:19-09D
Revision No. | Date | Page No. | Comments | Reason for changes
ASI-C006 | 2020-10-30 | C03.02 | Updated the demo limits along the edge of the perimeter road per field conditions verified by a construction progress topographic survey.
ASI-C006 | 2020-10-30 | C04.01 | Updated apron layout/geometry per field conditions verified by a construction progress topographic survey.
ASI-C006 | 2020-10-30 | C04.02 | Updated apron layout/geometry per field conditions verified by a construction progress topographic survey.
ASI-C006 | 2020-10-30 | C05.01 | Updated door locations on Hangar 1 to coordinate with revised architectural plans.
ASI-C006 | 2020-10-30 | C05.03 | Updated door locations on Hangar 3 to coordinate with revised architectural plans.
ASI-C006 | 2020-10-30 | C06.01 | Updated joint layout based on the minor apron layout/geometry changes.
ASI-C006 | 2020-10-30 | C06.02 | Updated joint layout based on the minor apron layout/geometry changes.
ASI-C006 | 2020-10-30 | C08.01 | Updated grading per field conditions verified by a construction progress topographic survey.
ASI-C006 | 2020-10-30 | C08.02 | Updated grading per field conditions verified by a construction progress topographic survey.
ASI-C006 | 2020-10-30 | C08.03 | Updated grading per field conditions verified by a construction progress topographic survey.
ASI-C006 | 2020-10-30 | C09.01 | Updated grading per field conditions verified by a construction progress topographic survey.
ASI-C006 | 2020-10-30 | C09.02 | Updated grading per field conditions verified by a construction progress topographic survey.
ASI-C006 | 2020-10-30 | C09.03 | Updated grading per field conditions verified by a construction progress topographic survey.
ASI-C006 | 2020-10-30 | C10.02 | Updated grading per field conditions verified by a construction progress topographic survey.
ASI-C006 | 2020-10-30 | C10.03 | Updated grading per field conditions verified by a construction progress topographic survey.
ASI-C006 | 2020-10-30 | C10.04 | Updated grading per field conditions verified by a construction progress topographic survey.
ASI-C006 | 2020-10-30 | C10.05 | Updated grading per field conditions verified by a construction progress topographic survey.
ASI-C006 | 2020-10-30 | C10.06 | Updated grading per field conditions verified by a construction progress topographic survey.
ASI-C006 | 2020-10-30 | C10.07 | Updated grading per field conditions verified by a construction progress topographic survey.
ASI-C006 | 2020-10-30 | C10.08 | Updated grading per field conditions verified by a construction progress topographic survey.
ASI-C006 | 2020-10-30 | C12.02 | Updated rim and top of grate elevations on storm structures per field conditions verified by a construction progress topographic survey.
ASI-C006 | 2020-10-30 | C12.03 | Updated rim and top of grate elevations on storm structures per field conditions verified by a construction progress topographic survey.
ASI-C006 | 2020-10-30 | C12.04 | Updated rim and top of grate elevations on storm structures per field conditions verified by a construction progress topographic survey. Also added a new storm sewer lateral and grate inlet to correspond with the revised grading.
ASI-C006 | 2020-10-30 | C12.09 | Added profile of the new storm sewer lateral
ASI-C006 | 2020-10-30 | C16.01 | Updated striping based on the minor apron layout/geometry changes
ASI-C006 | 2020-10-30 | C17.02 | Corrected callout and dimensions on the proposed gates on the driveway connecting to the fuel farm and the driveway connecting to George Haddaway Dr.
ASI-C006 | 2020-10-30 | C17.03 | Corrected dimensions on Detail 8
Formulas:
Galaxy FBO = [Galaxy FBO, row above]